## Project Planner
NSW Traffic Penalty Data Analysis Tool
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 60 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Initiation
Define Project Objective | 1 | 1 | 1 | 1 | 100%
Define Scope of Project | 2 | 1 | 2 | 1 | 100%
Define Constraints of Project | 3 | 1 | 3 | 1 | 100%
Define Team Roles and Responsibilities | 4 | 2 | 4 | 2 | 100%
Requirement Analysis
Gather Requirements | 6 | 1 | 6 | 1 | 100%
Analyse Dataset of NSW Traffic Penalty Data | 7 | 1 | 7 | 1 | 100%
Document Functional Requirement | 8 | 1 | 8 | 1 | 100%
Document Non-functional Requirement | 9 | 2 | 9 | 2 | 100%
Design and Planning
Design Architecture | 11 | 5 | 11 | 5 | 100%
Design User Interface | 16 | 5 | 16 | 5 | 100%
Implementation
Develop Basic Framework | 21 | 2 | 21 | 12 | 100%
Implement User-Selected Period Reporting | 23 | 3 | 33 | 6 | 100%
Implement Chart Distribution | 26 | 5 | 39 | 5 | 100%
Implement Radar/Camera Case Retrieval | 31 | 5 | 44 | 3 | 100%
Implement Mobile Phone Usage Analysis | 36 | 5 | 47 | 3 | 100%
Implement Penalty Amount Analysis | 41 | 5 | 50 | 3 | 100%
Testing and Validation
Develop Test Cases | 46 | 2 | 53 | 2 | 100%
Perform Unit Testing | 48 | 7 | 55 | 2 | 100%
Perform User Coverage Testing | 55 | 1 | 57 | 1 | 100%
Deployment & Project Wrap-up
Prepare Deployment Environment | 56 | 1 | 58 | 1 | 100%
Create User Documentation | 57 | 3 | 59 | 1 | 100%
Host All Resources on GitHub | 60 | 1 | 60 | 1 | 100%